## Human-GDPR
Risk ID | Description | Likelihood | Impact | Risk Rating | Owner | Mitigation Strategy | Residual Risk | Status
RH-1 | Staff sickness / absence | Likely | Medium | Medium High | Product owner/ Scrum master | Having a well informed team that can step in when needed, contingency planning for additional or sprint extension needs | Low Risk: Long term illnesses could impact team size and workloads | Ongoing
RH-2 | Non-GDPR Compliance MVP: video and audio from a volonteer is recorded and used outside of lawful basis | Likely | Severe | High | Project Owner | Contract and user information sheet with volunteers recording audio and videos | Low Risk | Ongoing
RH-3 | Single Point of Failure / Staff Training | Possible | Severe | Medium High | Project Owner | Making sure all staff have relevant onboarding / training concerned with what they're involved with. | Medium Risk: Staff having equal or relevant training to all involved lowers the chance of a single point of failure - if the most knowledgable person is absent then the prokect can stall. | Ongoing
RH-4 | Team goes down to 2 active developers (the threshold for a project being shut down is when it goes down to 1 developer) | Possible | Severe | Medium High | Team Lead | Keep roles open for new developers, create clear LO mapping for students, keep advertising new tasks to students | Medium Risk: Cannot predict if students will be interested in joining | Ongoing
RH-5 | Repository is compromised by a wrong action (force push to development or deployment branches, repo is deleted by mistake, PR are merged without reviews) | Possible | Severe | Medium High | Team Lead | Ensure principal of least principal is enforced. Don't give access to significant sectors to individuals that don't explicitly need it. Github rulset and branch protection on development and deployment | Low risk | Ongoing
RH-6 | New developer or developer doesn't know the technology used | Likely | Significant | Medium High | Product owner/ Scrum master | Try to ensure all staff recieve proper training and have access to learning recourses. Perpahs hold training spikes. | Low Risk: Developers don't follow the training | Ongoing
RH-7 | Single Point of Failure / Management | Very Unlikey | Severe | Medium High | Project Owner | Define Scrum roles, delegate outcome responsibilities to ticket owners, code of conduct document, joint presentation creation and delivery, multiple admin roles for essential resources | Low Risk: Students might not feel compelled to keep the project alive without project owner | Ongoing
RH-8 | Mishandling of API Keys / Tokens | Very Unlikely | Severe | Medium High | Project Owner | Staff security training, security workflows and procedures | Low Risk: Developers don't follow the training | Ongoing
RH-9 | Mishandling of Administrator accounts | Unlikely | Severe | Medium | Project Owner | Require MFA for privileged accounts, use separate admin roles and audit changes | Low Risk | Ongoing